## Dataset 4
№ | ID | Link | Article | Country | Year | Stage | Effects per project | Estimation | Unified metric | Score to the unified metric | Calculations | DCF influence | Comment | Supportive links for the unified metrics
1 | A0001 | https://www.pci.org/PCI_Docs/Publications/PCI%20Journal/2003/May-June/Process%20Improvements%20in%20Precast%20Concrete%20Construction%20Using%20Top-Down%20Parametric%203-D%20Computer%20Modeling.pdf | Sacks et al. (2003) | Israel | 2003 | 1_Design | Reduction in the number of the design errors | 50% | Reduction in the number of the design errors | 1.28% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,2_CAPEX reduction | Design stage_CAPEX | Reduction of the number of the design errors on the design stage | (пусто)
2 | A0002 | https://www.researchgate.net/publication/341242142_A_FRAMEWORK_FOR_EVALUATING_AN_INTEGRATED_BIM_ROI_BASED_ON_PREVENTING_REWORK_IN_THE_CONSTRUCTION_PHASE#read | Sacks et al. (2005) | Israel | 2005 | 2_Construction | Increase in productivity | 2.3% | Reduction in the construction schedule | 2.3% | 1:1 | Construction stage schedule | The time, which is needed for the constraction, can decrease due to BIM | (пусто)
3 | A0003 | https://www.researchgate.net/publication/237470054_Benefits_and_lessons_learned_of_implementing_Building_Virtual_Design_and_Construction_VDC_technologies_for_coordination_of_Mechanical_Electrical_and_Plumbing_MEP_systems_on_a_large_Healthcare_project | Khanzode et al. (2008) | USA | 2008 | 2_Construction | BIM approach saved project value | 7.69% | Reduction in the total project construction value | 7.69% | 1:1 | Construction stage_CAPEX | The time, which is needed for the constraction, can decrease due to BIM | (пусто)
4 | A0004 | https://www.researchgate.net/publication/237470054_Benefits_and_lessons_learned_of_implementing_Building_Virtual_Design_and_Construction_VDC_technologies_for_coordination_of_Mechanical_Electrical_and_Plumbing_MEP_systems_on_a_large_Healthcare_project | Khanzode et al. (2008) | USA | 2008 | 2_Construction | Reduction time of the schedule | 13% | Reduction in time of the construction schedule | 13% | 1:1 | Construction stage schedule | The time, which is needed for the constraction, can decrease due to BIM | (пусто)
5 | A0005 | https://pdf.sciencedirectassets.com/271427/1-s2.0-S0926580508X00020/1-s2.0-S0926580507001082/main.pdf?X-Amz-Security-Token=IQoJb3JpZ2luX2VjEKH%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaCXVzLWVhc3QtMSJIMEYCIQDQYmXRhfuBGCFrhvMfnih4R6sJPeVWWzNUcr%2BChPNG2gIhAIINKB%2Ffx%2BJLBhCqOk%2B2dI3Om0fzLAzj4XsGz2K4dsQQKrMFCGoQBRoMMDU5MDAzNTQ2ODY1IgzW5iYQMgy1hkCEUVwqkAXhQwtajj4MAyZqBpmDVWRDmNAiyLTLoYRKAKyItGgiSQgVsUXJb47x%2FLNRCPf8oodbCbnUisz02Rb85DUkn4Vs6SFp%2BFwFjd%2FKQJHxj9BK2Ra8AHXSQiYPAby%2BdhQ1v2WM06kVPoPdnjiQNyQHhX5a9%2BA4%2Fnz2QCEgjFgCZ8IVYw80y2DH7x%2BAFZr4UP1F7dUS9qJCZQ9WoXMyAHuwPHJK2p2n%2B6HkGd776XQi7K57rg%2FLn7%2B9pdi8zjki7EA9FOmF%2FvMaTobYqLG%2FB%2B5zu7jXW7PPk3DwE60DymRDxVzBwD5xtNMuY6819Ay2sDWIF%2Flr4f3gL5IcE9JuiVF2y5ySspT90RyXHhNoFFlrnMqPv5YsgMKypGSfzJNpSgQ0k%2B5E%2B6RZRNNF9JYrT5kvFLFInTFWsoGNujUdRrcjP11SmqW8UiJDNWy5k%2Bl5FM3T4mDIPhnSJczmEmUlu1X98jdOstBY0DmOGkrv%2BpVz8rspOU2ma7F8KP6PjvSsekwczB3yl3pG8arkAWATjcZpzes04PNLjHpisn0muLcu%2FGaSElRBewttCnovKzbYxJhBkJ6bvCswwWiwAwKVwEbzvHGzHtKNJpeTb2yQ1IeybHWx%2FPnHNWXWEPgZ2zggAGJIeDngBT0Foc20CY2mRKdhniqMcBTSag8q9VihJdBlYlKvwtzsQvBgx6Fr%2BfYISOiZE104FnLPgMsN9CmfSgL1sDFl1pMgmMoOEFc2xiFrc8z%2B0yXESA61H5c1bQ6a56NPGmVookgM7itmZZHYUqyWOCCeknt%2FIDkBm4VqdaUH%2FA30eudtF%2BR6NJ%2BnaSoBO3Y2TzXZxfHUUcP7oFwRBrIs8rbrWuxYms6Uko%2Fz8aPLFYxEwzDM4JXJBjqwAcGGqDTx1q4jsUuK0OVYtnQcllTgQOuE4g%2FjqVEH7iiBMkoGOBwd1ee4BO5qd%2BDm7RKI%2FaANXrohyPUC%2B8vYjWHfGe9qSIEB05emWK64eYcDCttigXj%2FbaK7n%2FCgWmmvGPBCZe5Pb02%2BwfZfabAg8d8To6ekhtVGGjWjYj5Ebf1iCVRsLzGhUfr9L2xcwWTEFsB%2FFe0deqCZATbZEEG6LOxUngLDefGWxhBIONaG13cX&X-Amz-Algorithm=AWS4-HMAC-SHA256&X-Amz-Date=20251125T101235Z&X-Amz-SignedHeaders=host&X-Amz-Expires=300&X-Amz-Credential=ASIAQ3PHCVTYWKQ3ZYNC%2F20251125%2Fus-east-1%2Fs3%2Faws4_request&X-Amz-Signature=30a1c685970dc0f3f148a3db0c2cacc9b666e5c443ba7e06163e13325a4dab5a&hash=71d82162fcb4c51000f168ca4237be8d7a736e343f7d52a2069d8be026d3c773&host=68042c943591013ac2b2430a89b270f6af2c76d8dfd086a07176afe7c76c2c61&pii=S0926580507001082&tid=spdf-ee7e3edd-9db4-496d-bb50-2b7cc6643b36&sid=6249dfa59c2b8043cd0be979bd7f51776698gxrqb&type=client&tsoh=d3d3LnNjaWVuY2VkaXJlY3QuY29t&rh=d3d3LnNjaWVuY2VkaXJlY3QuY29t&ua=010457075a53510a5601&rr=9a405e5b4fd3ef52&cc=gb | Sacks and Barak (2008) | Israel | 2008 | 1_Design | Increase in productivity | 15% | Reduction in time to complete the design stage | 15% | 1:1 | Design stage schedule | fewer hours spent on drawing production | (пусто)
6 | A0006 | https://pdf.sciencedirectassets.com/271427/1-s2.0-S0926580508X00020/1-s2.0-S0926580507001082/main.pdf?X-Amz-Security-Token=IQoJb3JpZ2luX2VjEKH%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaCXVzLWVhc3QtMSJIMEYCIQDQYmXRhfuBGCFrhvMfnih4R6sJPeVWWzNUcr%2BChPNG2gIhAIINKB%2Ffx%2BJLBhCqOk%2B2dI3Om0fzLAzj4XsGz2K4dsQQKrMFCGoQBRoMMDU5MDAzNTQ2ODY1IgzW5iYQMgy1hkCEUVwqkAXhQwtajj4MAyZqBpmDVWRDmNAiyLTLoYRKAKyItGgiSQgVsUXJb47x%2FLNRCPf8oodbCbnUisz02Rb85DUkn4Vs6SFp%2BFwFjd%2FKQJHxj9BK2Ra8AHXSQiYPAby%2BdhQ1v2WM06kVPoPdnjiQNyQHhX5a9%2BA4%2Fnz2QCEgjFgCZ8IVYw80y2DH7x%2BAFZr4UP1F7dUS9qJCZQ9WoXMyAHuwPHJK2p2n%2B6HkGd776XQi7K57rg%2FLn7%2B9pdi8zjki7EA9FOmF%2FvMaTobYqLG%2FB%2B5zu7jXW7PPk3DwE60DymRDxVzBwD5xtNMuY6819Ay2sDWIF%2Flr4f3gL5IcE9JuiVF2y5ySspT90RyXHhNoFFlrnMqPv5YsgMKypGSfzJNpSgQ0k%2B5E%2B6RZRNNF9JYrT5kvFLFInTFWsoGNujUdRrcjP11SmqW8UiJDNWy5k%2Bl5FM3T4mDIPhnSJczmEmUlu1X98jdOstBY0DmOGkrv%2BpVz8rspOU2ma7F8KP6PjvSsekwczB3yl3pG8arkAWATjcZpzes04PNLjHpisn0muLcu%2FGaSElRBewttCnovKzbYxJhBkJ6bvCswwWiwAwKVwEbzvHGzHtKNJpeTb2yQ1IeybHWx%2FPnHNWXWEPgZ2zggAGJIeDngBT0Foc20CY2mRKdhniqMcBTSag8q9VihJdBlYlKvwtzsQvBgx6Fr%2BfYISOiZE104FnLPgMsN9CmfSgL1sDFl1pMgmMoOEFc2xiFrc8z%2B0yXESA61H5c1bQ6a56NPGmVookgM7itmZZHYUqyWOCCeknt%2FIDkBm4VqdaUH%2FA30eudtF%2BR6NJ%2BnaSoBO3Y2TzXZxfHUUcP7oFwRBrIs8rbrWuxYms6Uko%2Fz8aPLFYxEwzDM4JXJBjqwAcGGqDTx1q4jsUuK0OVYtnQcllTgQOuE4g%2FjqVEH7iiBMkoGOBwd1ee4BO5qd%2BDm7RKI%2FaANXrohyPUC%2B8vYjWHfGe9qSIEB05emWK64eYcDCttigXj%2FbaK7n%2FCgWmmvGPBCZe5Pb02%2BwfZfabAg8d8To6ekhtVGGjWjYj5Ebf1iCVRsLzGhUfr9L2xcwWTEFsB%2FFe0deqCZATbZEEG6LOxUngLDefGWxhBIONaG13cX&X-Amz-Algorithm=AWS4-HMAC-SHA256&X-Amz-Date=20251125T101235Z&X-Amz-SignedHeaders=host&X-Amz-Expires=300&X-Amz-Credential=ASIAQ3PHCVTYWKQ3ZYNC%2F20251125%2Fus-east-1%2Fs3%2Faws4_request&X-Amz-Signature=30a1c685970dc0f3f148a3db0c2cacc9b666e5c443ba7e06163e13325a4dab5a&hash=71d82162fcb4c51000f168ca4237be8d7a736e343f7d52a2069d8be026d3c773&host=68042c943591013ac2b2430a89b270f6af2c76d8dfd086a07176afe7c76c2c61&pii=S0926580507001082&tid=spdf-ee7e3edd-9db4-496d-bb50-2b7cc6643b36&sid=6249dfa59c2b8043cd0be979bd7f51776698gxrqb&type=client&tsoh=d3d3LnNjaWVuY2VkaXJlY3QuY29t&rh=d3d3LnNjaWVuY2VkaXJlY3QuY29t&ua=010457075a53510a5601&rr=9a405e5b4fd3ef52&cc=gb | Sacks and Barak (2008) | Israel | 2008 | 1_Design | Increase in productivity | 41% | Reduction in time to complete the design stage | 41% | 1:1 | Design stage schedule | fewer hours spent on drawing production | (пусто)
7 | A0008 | http://www.engineering.nottingham.ac.uk/icccbe/proceedings/pdf/pf77.pdf | Giel and Issa (2011) | USA | 2011 | 2_Construction | ROI | 36.7% | Return on investments (1) | 36.7% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
8 | A0009 | http://www.engineering.nottingham.ac.uk/icccbe/proceedings/pdf/pf77.pdf | Giel and Issa (2011) | USA | 2011 | 2_Construction | ROI | 16.2% | Return on investments (1) | 16.2% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
9 | A0010 | http://www.engineering.nottingham.ac.uk/icccbe/proceedings/pdf/pf77.pdf | Giel and Issa (2011) | USA | 2011 | 2_Construction | ROI | 300% | Return on investments (1) | 300% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
10 | A0011 |  | Williams (2011) | USA | 2011 | 1_Design | Reduction in the number of changes of orders | 47% | Reduction in the number of changes of orders | 1.203% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | Decrease in the number of changes, which are motivated by stakeholders, PM and engineers | (пусто)
11 | A0012 | https://ascelibrary.org/doi/10.1061/%28ASCE%29LM.1943-5630.0000127 | Azhar S. (2011) | USA | 2011 | 2_Construction | Reduction of budget overrun of total project value | 40% | Reduction in the overrun of the total project construction value | 40% | 1:1 | Construction stage_CAPEX overrun |  | (пусто)
12 | A0013 | https://ascelibrary.org/doi/10.1061/%28ASCE%29LM.1943-5630.0000127 | Azhar S. (2011) | USA | 2011 | 1_Design | Costs saved due to findings of design errors | 10% | Reduction in the overrun of the total project construction value | 0.256% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,2_CAPEX reduction | Design stage_CAPEX |  | (пусто)
13 | A0014 | https://ascelibrary.org/doi/10.1061/%28ASCE%29LM.1943-5630.0000127 | Azhar S. (2011) | USA | 2011 | 2_Construction | Reduction time of the schedule | 7% | Reduction in time of the construction schedule | 7% | 1:1 | Construction stage schedule | The time, which is needed for the constraction, can decrease due to BIM | (пусто)
14 | A0015 | https://ascelibrary.org/doi/10.1061/%28ASCE%29LM.1943-5630.0000127 | Azhar S. (2011) | USA | 2011 | 1_Design | Costs saved due to findings of design errors | 0.43% | Reduction in the overrun of the total project construction value | 0.01101% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,2_CAPEX reduction | Design stage_CAPEX |  | (пусто)
15 | A0016 | https://ascelibrary.org/doi/10.1061/%28ASCE%29LM.1943-5630.0000127 | Azhar S. (2011) | USA | 2011 | 1_Design | ROI | 634% | Return on investments (1) | 634% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
16 | A0018 | https://pdf.sciencedirectassets.com/271427/1-s2.0-S0926580512X00025/1-s2.0-S0926580511002287/main.pdf?X-Amz-Security-Token=IQoJb3JpZ2luX2VjEHMaCXVzLWVhc3QtMSJHMEUCIQCTHxmV4bjR%2FdmMCgG%2B7JxbH3qaql1XFYJYiWLxOjxH4wIgOFpq2Ms5iK%2FXu0Evh5YdtReJuup0Zp8UWYJq0KeKc04qswUIOxAFGgwwNTkwMDM1NDY4NjUiDJbTzi6Yk0n%2FY0OTtiqQBbuzjQ1HafqleC6K7XYZytcb0hLraJ2BykDtf1ls4GmtJRWZNgZA0qqIQ0kHueS9peL8y2Ti%2BT%2FJEuJER%2BeSdWju9%2B2U4VAa8vNG%2FTIXbpjpLe8QXXRbaLtHWTvTEf5poUPCWkynoxLK5PRYeGtsGQPSrScYhUX1xX62G05Rwl%2Fi%2FS0hbUtKfVVLGgbMy%2FqvuDi5o6B6RSR%2F5QVSYvtXaZNwqGBFLpMANG7VB5%2BhV1xt0ZhTo1kWmsGqr%2BupZfUfMa3WawlR%2BGo3CTbDhwIWu7SePX6Va2RmPMBW89sHfjMHjaSw0bqg6QxTYNd%2FhiQUagSdwlWlPzTxdEIcJ4dvr24yvtu9vHlqIyGg712h7OzFkcpPkao20YeodZPOHA9jBFcFRs8PDovrdk3Chr33tgB5tu%2FIExWEBLQxgPqw0pQHNPjul1%2F77WjTzlHnBu%2FIoFuAmFhHjSKQGtEZfVI%2FGOURQ8kyH6wL8PoCdWwx%2FT8TNUxcLimEepZGxMLdJIDbhTrcE0fkg2zvgxxAdUHnnLMXNY9hR7FClvbXbtB%2Fme1ElvT40j1YK1FvQNmZHeprUlsury%2FIBBShat4hP4dlBtLW5tcSaw497b2rdn%2BV5SqooQ8bnw7qpwTC9iV28d0L2QxR1azs2vXxwC1Ee6suzZBY6DnA6PdCLEBdDVuAELypsPd3IV7rqUB0MAUnq3F8T%2FcP0AFCm74xRrtY6MgS3ISeckKTHda19u20ycgNByC%2ByNXATaVB146SL8zvDkV9SufDtMQjjMyItj9gOFhcD0FSU46MkKE10jiwM7gQ7EyfKNNFqZPrD3tqJhpzXJdvn4qcNXKbBK80w9IkBcNQMoZnY%2FhPKN55XqhjyGCNFrfyMOq%2Fi8kGOrEBTlgtxlQ1dS51fIgY7Ebvy%2BMd4T4BgWg%2FrW1fmmSGzlfXUH0M7GKZXkr5ZzCgUcJkeyN3MYMwr1N3o82EDZDsSjvqWBuBHERpIlrB9Zx2dfVfhRcxchCP0j8ib8eFq2Gio4B1tY6t%2FKG1Qgqq3ChrGhm9aWYvdqsV5V5mYTDANqWGyA40zcSPFaPi6C8HRtP4pR%2FIVXN8NOwVtGggh8gi9wc9plkiSYLyUpFhjPTmD1PT&X-Amz-Algorithm=AWS4-HMAC-SHA256&X-Amz-Date=20251123T111333Z&X-Amz-SignedHeaders=host&X-Amz-Expires=300&X-Amz-Credential=ASIAQ3PHCVTYZUCS4NF5%2F20251123%2Fus-east-1%2Fs3%2Faws4_request&X-Amz-Signature=3e5ca22e56272c6ee64bcd7ca67b90c91a902b784650a673808cacac4486fed3&hash=23123c42ff3c765086dcf9a096891f27921083503cb8c90f1ee51ff46557061b&host=68042c943591013ac2b2430a89b270f6af2c76d8dfd086a07176afe7c76c2c61&pii=S0926580511002287&tid=spdf-c98819ce-82ba-4452-b04c-04a860e52dab&sid=307ace4a9ca7c24e7c09396891e5077dde20gxrqb&type=client&tsoh=d3d3LnNjaWVuY2VkaXJlY3QuY29t&rh=d3d3LnNjaWVuY2VkaXJlY3QuY29t&ua=01045602555056030157&rr=9a303ce85fe0cd9d&cc=gb | Lee et al. (2012) | South Korea | 2012 | 1_Design | ROI | 63% | Return on investments (1) | 63% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
17 | A0019 | https://damassets.autodesk.net/content/dam/autodesk/www/solutions/building-information-modeling/bim-value/mhc-business-value-of-bim-in-north-america.pdf | McGraw-Hill (2012) | Canada | 2012 | 2_Construction | Reduction of budget overrun of total project value | 10% | Reduction in the overrun of the total project construction value | 10% | 1:1 | Construction stage_CAPEX overrun |  | (пусто)
18 | A0020 | https://doi.org/10.1016/j.autcon.2012.02.00 | Barlish and Sullivan (2012) | USA | 2012 | 2_Construction | Reduction in time of the schedule delay | 67% | Reduction in time of the construction schedule delay | 67% | 1:1 | Construction stage schedule_delay | The delay can be avoided due to the use of BIM | (пусто)
19 | A0021 | https://nrc-publications.canada.ca/eng/view/ft/?id=af0db2c8-8d85-4e26-b584-f51ae0fa9eb5 | Neelamkavil and Ahmed (2012) | Canada | 2012 | 2_Construction | Reduction in number of Request of information | 37% | Reduction in number of RFI | 0.592% | 1,6% of CAPEX is RFI_CAPEX reduction | Construction stage_CAPEX | A RFI is a formal written process in which parties clarify information gaps in construction documents (McGraw-Hill, 2008). Incomplete, unclear or outdated technical specifications, and the lack of buildability result in continuous RFIs thereby, interruptions to the work progress (Jarkas and Bitar, 2012; Rivas et al., 2011; Hasan et al., 2018). This creates friction between the architect/engineers and the contractor | https://www.naiop.org/research-and-publications/magazine/2022/summer-2022/development-ownership/how-rfis-and-change-orders-disrupt-multifamily-development-projects/ assume from that RFI is 1,6% of the project cost
20 | A0022 | https://nrc-publications.canada.ca/eng/view/ft/?id=af0db2c8-8d85-4e26-b584-f51ae0fa9eb5 | Neelamkavil and Ahmed (2012) | Canada | 2012 | 1_Design | Reduction in the number of changes of orders | 32% | Reduction in the number of changes of orders | 0.8192% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | A change order is usually the result of an owner-initiated change in the scope or time frame of a project, unforeseen conditions that require change, or a design error/omission that results in change | (пусто)
21 | A0023 | https://nrc-publications.canada.ca/eng/view/ft/?id=af0db2c8-8d85-4e26-b584-f51ae0fa9eb5 | Neelamkavil and Ahmed (2012) | Canada | 2012 | 2_Construction | Reduction in time of the schedule delay | 50% | Reduction in time of the construction schedule delay | 50% | 1:1 | Construction stage schedule_delay | The delay can be avoided due to the use of BIM | (пусто)
22 | A0024 | https://nrc-publications.canada.ca/eng/view/ft/?id=af0db2c8-8d85-4e26-b584-f51ae0fa9eb5 | Neelamkavil and Ahmed (2012) | Canada | 2012 | 1_Design | Reduction in the number of changes of orders | 5% | Reduction in the number of changes of orders | 0.128% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | A change order is usually the result of an owner-initiated change in the scope or time frame of a project, unforeseen conditions that require change, or a design error/omission that results in change | (пусто)
23 | A0025 | https://nrc-publications.canada.ca/eng/view/ft/?id=af0db2c8-8d85-4e26-b584-f51ae0fa9eb5 | Neelamkavil and Ahmed (2012) | Canada | 2012 | 1_Design | Increase in productivity | 37% | Reduction in time to complete the design stage | 37% | 1:1 | Design stage schedule | fewer hours spent on drawing production | (пусто)
24 | A0026 | https://nrc-publications.canada.ca/eng/view/ft/?id=af0db2c8-8d85-4e26-b584-f51ae0fa9eb5 | Neelamkavil and Ahmed (2012) | Canada | 2012 | 1_Design | Time savings in design stage | 20% | Reduction in time to complete the design stage | 20% | 1:1 | Design stage schedule | 100% - Time with BIM / Time without BIM | (пусто)
25 | A0027 | https://ascelibrary.org/doi/abs/10.1061/(ASCE)CP.1943-5487.0000164 | Giel and Issa (2013) | USA | 2013 | 1_Design | Reduction in the number of changes of orders | 40% | Reduction in the number of changes of orders | 1.024% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | A change order is usually the result of an owner-initiated change in the scope or time frame of a project, unforeseen conditions that require change, or a design error/omission that results in change | (пусто)
26 | A0028 | https://ascelibrary.org/doi/abs/10.1061/(ASCE)CP.1943-5487.0000164 | Giel and Issa (2013) | USA | 2013 | 1_Design | Reduction in the number of changes of orders | 48% | Reduction in the number of changes of orders | 1.229% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | A change order is usually the result of an owner-initiated change in the scope or time frame of a project, unforeseen conditions that require change, or a design error/omission that results in change | (пусто)
27 | A0029 | https://ascelibrary.org/doi/abs/10.1061/(ASCE)CP.1943-5487.0000164 | Giel and Issa (2013) | USA | 2013 | 1_Design | Reduction in the number of changes of orders | 37% | Reduction in the number of changes of orders | 0.9472% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | A change order is usually the result of an owner-initiated change in the scope or time frame of a project, unforeseen conditions that require change, or a design error/omission that results in change | (пусто)
28 | A0030 | https://ascelibrary.org/doi/abs/10.1061/(ASCE)CP.1943-5487.0000164 | Giel and Issa (2013) | USA | 2013 | 2_Construction | Reduction in number of Request of information | 34% | Reduction in number of RFI | 0.544% | 1,6% of CAPEX is RFI_CAPEX reduction | Construction stage_CAPEX | A RFI is a formal written process in which parties clarify information gaps in construction documents (McGraw-Hill, 2008). Incomplete, unclear or outdated technical specifications, and the lack of buildability result in continuous RFIs thereby, interruptions to the work progress (Jarkas and Bitar, 2012; Rivas et al., 2011; Hasan et al., 2018). This creates friction between the architect/engineers and the contractor | https://www.naiop.org/research-and-publications/magazine/2022/summer-2022/development-ownership/how-rfis-and-change-orders-disrupt-multifamily-development-projects/ assume from that RFI is 1,6% of the project cost
29 | A0031 | https://ascelibrary.org/doi/abs/10.1061/(ASCE)CP.1943-5487.0000164 | Giel and Issa (2013) | USA | 2013 | 2_Construction | Reduction in number of Request of information | 68% | Reduction in number of RFI | 1.088% | 1,6% of CAPEX is RFI_CAPEX reduction | Construction stage_CAPEX | A RFI is a formal written process in which parties clarify information gaps in construction documents (McGraw-Hill, 2008). Incomplete, unclear or outdated technical specifications, and the lack of buildability result in continuous RFIs thereby, interruptions to the work progress (Jarkas and Bitar, 2012; Rivas et al., 2011; Hasan et al., 2018). This creates friction between the architect/engineers and the contractor | https://www.naiop.org/research-and-publications/magazine/2022/summer-2022/development-ownership/how-rfis-and-change-orders-disrupt-multifamily-development-projects/ assume from that RFI is 1,6% of the project cost
30 | A0032 | https://ascelibrary.org/doi/abs/10.1061/(ASCE)CP.1943-5487.0000164 | Giel and Issa (2013) | USA | 2013 | 2_Construction | Reduction in number of Request of information | 43% | Reduction in number of RFI | 0.688% | 1,6% of CAPEX is RFI_CAPEX reduction | Construction stage_CAPEX | A RFI is a formal written process in which parties clarify information gaps in construction documents (McGraw-Hill, 2008). Incomplete, unclear or outdated technical specifications, and the lack of buildability result in continuous RFIs thereby, interruptions to the work progress (Jarkas and Bitar, 2012; Rivas et al., 2011; Hasan et al., 2018). This creates friction between the architect/engineers and the contractor | https://www.naiop.org/research-and-publications/magazine/2022/summer-2022/development-ownership/how-rfis-and-change-orders-disrupt-multifamily-development-projects/ assume from that RFI is 1,6% of the project cost
31 | A0033 | https://ascelibrary.org/doi/abs/10.1061/(ASCE)CP.1943-5487.0000164 | Giel and Issa (2013) | USA | 2013 | 2_Construction | ROI | 16% | Return on investments (1) | 16% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
32 | A0034 | https://doi.org/10.1016/j.autcon.2013.05.008 | Love et al. (2013) | Australia | 2013 | 2_Construction | Reduction in time of the schedule delay | 7% | Reduction in time of the construction schedule delay | 7% | 1:1 | Construction stage schedule_delay | The delay can be avoided due to the use of BIM | (пусто)
33 | A0035 | https://ir-api.ua.edu/api/core/bitstreams/0741d860-e466-407b-a3ff-84d2b2a696e6/content | Bruhn III (2014) | USA | 2014 | 1_Design | Reduction in the number of changes of orders | 80% | Reduction in the number of changes of orders | 2.048% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | A change order is usually the result of an owner-initiated change in the scope or time frame of a project, unforeseen conditions that require change, or a design error/omission that results in change | (пусто)
34 | A0036 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 1_Design | ROI | 1.704% | Return on investments (2) | 1.704% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
35 | A0037 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 1_Design | ROI | 1.6% | Return on investments (2) | 1.6% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
36 | A0038 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 1_Design | ROI | 1.736% | Return on investments (2) | 1.736% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
37 | A0039 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 1_Design | ROI | 0.72% | Return on investments (2) | 0.72% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
38 | A0040 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 1_Design | ROI | 3.88% | Return on investments (2) | 3.88% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
39 | A0041 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 1_Design | ROI | 4.2% | Return on investments (2) | 4.2% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
40 | A0045 | https://www.researchgate.net/publication/283985475_BIM_perspective_definition_metadata_for_interworking_facility_management_data | Kang and Choi (2015) | South Korea | 2015 | 3_Operation | Increase in finding and sharing asset information | 25% | Annual reduction in salary expenditures | 5% | 20% of working time is searching info | Salary |  | https://bloomfire.com/blog/roi-knowledge-management/
41 | A0046 | https://www.researchgate.net/publication/325502466_Economic_Analysis_of_Design_Errors_in_BIM-Based_High-Rise_Construction_Projects_Case_Study_of_Haeundae_L_Project | Ham et al. (2018) | South Korea | 2018 | 1_Design | ROI | 94.41% | Return on investments (1) | 94.41% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
42 | A0048 | https://www.cdbb.cam.ac.uk/files/3._pwc_benefits_measurement_methodology.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 3_Operation | Increase in finding and sharing asset information | 70% | Annual reduction in salary expenditures | 14% | 20% of working time is searching info | Salary |  | https://www.cincopa.com/blog/how-to-calculate-the-roi-of-knowledge-sharing/
43 | A0049 | https://www.cdbb.cam.ac.uk/files/3._pwc_benefits_measurement_methodology.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 2_Construction | Reduction in the number of the design errors | 20% | Reduction in the number of the design errors | 0.512% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,2_CAPEX reduction | Construction stage_CAPEX |  | (пусто)
44 | A0050 | https://www.cdbb.cam.ac.uk/files/3._pwc_benefits_measurement_methodology.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 2_Construction | Costs saved due to findings of design errors | 0.25% | Reduction in the overrun of the total project construction value | 0.0064% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,2_CAPEX reduction | Construction stage_CAPEX overrun |  | (пусто)
45 | A0051 | https://www.cdbb.cam.ac.uk/files/4.pwcbmmapplicationreport_0.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 3_Operation | Cost saving in asset maintenance | 4.4% | Annual reduction in maintance expenditures | 4.4% | 1:1 | Maintenance obligations | cost saving / operation opex | (пусто)
46 | A0053 | https://www.cdbb.cam.ac.uk/files/4.pwcbmmapplicationreport_0.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 3_Operation | Cost saving in asset maintenance | 6.5% | Annual reduction in maintance expenditures | 6.5% | 1:1 | Maintenance obligations | cost saving / operation opex | (пусто)
47 | A0054 | https://www.cdbb.cam.ac.uk/files/4.pwcbmmapplicationreport_0.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 1_Design | Cost savings in design stage | 3.77% | Reduction in cost of the design stage | 4% | 1:1 | Design stage_CAPEX |  | (пусто)
48 | A0055 | https://www.cdbb.cam.ac.uk/files/4.pwcbmmapplicationreport_0.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 2_Construction | Cost saving in build and commision | 0.84% | Reduction in the total project construction value | 0.84% | 1:1 | Construction stage_CAPEX |  | (пусто)
49 | A0056 | https://www.cdbb.cam.ac.uk/files/4.pwcbmmapplicationreport_0.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 1_Design | Cost savings in design stage | 5.29% | Reduction in cost of the design stage | 5% | 1:1 | Design stage_CAPEX |  | (пусто)
50 | A0057 | https://www.cdbb.cam.ac.uk/files/4.pwcbmmapplicationreport_0.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 2_Construction | Cost saving in build and commision | 0.03% | Reduction in the total project construction value | 0.03% | 1:1 | Construction stage_CAPEX |  | (пусто)
51 | A0058 | https://www.cdbb.cam.ac.uk/files/4.pwcbmmapplicationreport_0.pdf | PWC BIM Level 2 Benefits Measurement (2018) | UK | 2018 | 2_Construction | Cost saving from identifying clash detection | 0.05% | Reduction in the overrun of the total project construction value | 0.00512% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,8_CAPEX reduction | Construction stage_CAPEX overrun |  | (пусто)
52 | A0059 | https://www.researchgate.net/publication/341242142_A_FRAMEWORK_FOR_EVALUATING_AN_INTEGRATED_BIM_ROI_BASED_ON_PREVENTING_REWORK_IN_THE_CONSTRUCTION_PHASE | Lee et al. (2019) | South Korea | 2019 | 2_Construction | Reduction of rework costs | 63% | Reduction in the cost of the rework | 6.451% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:1_CAPEX reduction | Construction stage_CAPEX | Due to the change of order rework needs to be done | https://www.naiop.org/research-and-publications/magazine/2022/summer-2022/development-ownership/how-rfis-and-change-orders-disrupt-multifamily-development-projects/ assume from that CoO is 12,8% of the project cost
53 | A0060 | https://www.researchgate.net/publication/341242142_A_FRAMEWORK_FOR_EVALUATING_AN_INTEGRATED_BIM_ROI_BASED_ON_PREVENTING_REWORK_IN_THE_CONSTRUCTION_PHASE | Lee et al. (2019) | South Korea | 2019 | 2_Construction | ROI | 476% | Return on investments (1) | 476% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
54 | A0061 | https://journals.vilniustech.lt/index.php/JCEM/article/view/12611 | Conde et al. (2020) | Spain | 2020 | 1_Design | Reduction in time to complete the design stage | 20% | Reduction in time to complete the design stage | 20% | 1:1 | Design stage schedule | 100% - Time with BIM / Time without BIM | (пусто)
55 | A0062 | https://journals.vilniustech.lt/index.php/JCEM/article/view/12611 | Conde et al. (2020) | Spain | 2020 | 1_Design | Reduction in number of Request of information | 25% | Reduction in number of RFI | 0.4% | 1,6% of CAPEX is RFI_CAPEX reduction | Construction stage_CAPEX | A RFI is a formal written process in which parties clarify information gaps in construction documents (McGraw-Hill, 2008). Incomplete, unclear or outdated technical specifications, and the lack of buildability result in continuous RFIs thereby, interruptions to the work progress (Jarkas and Bitar, 2012; Rivas et al., 2011; Hasan et al., 2018). This creates friction between the architect/engineers and the contractor | https://www.naiop.org/research-and-publications/magazine/2022/summer-2022/development-ownership/how-rfis-and-change-orders-disrupt-multifamily-development-projects/ assume from that RFI is 1,6% of the project cost
56 | A0063 | https://journals.vilniustech.lt/index.php/JCEM/article/view/12611 | Conde et al. (2020) | Spain | 2020 | 1_Design | ROI | 42% | Return on investments (1) | 42% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
57 | A0064 | https://www.tandfonline.com/doi/full/10.1080/13467581.2020.1800471 | Kim et al. (2020) | South Korea | 2020 | 2_Construction | ROI | 145% | Return on investments (1) | 145% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
58 | A0065 | https://www.tandfonline.com/doi/full/10.1080/13467581.2020.1800471 | Kim et al. (2020) | South Korea | 2020 | 2_Construction | ROI | 350% | Return on investments (1) | 350% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
59 | A0066 | https://journals.vilniustech.lt/index.php/JCEM/article/view/12185 | Lee and Lee (2020) | South Korea | 2020 | 2_Construction | ROI | 167% | Return on investments (1) | 167% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
60 | A0067 | https://doi.org/10.36680/j. itcon.2020.009. [41] H. Feng, M. Kassem, D. Gr | Abdelbary et al. (2020) | UK | 2020 | 1_Design | Improvement in coordination between different departments | 6% | Reduction in time to complete the design stage | 0.6% | Assumption: 10% of design budget is the amount on the coordination | Design stage schedule | fewer hours spent on drawing production | (пусто)
61 | A0068 | https://doi.org/10.36680/j. itcon.2020.009. [41] H. Feng, M. Kassem, D. Gr | Abdelbary et al. (2020) | UK | 2020 | 1_Design | Reduction in the number of changes of orders | 47% | Reduction in the number of changes of orders | 1.203% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | A change order is usually the result of an owner-initiated change in the scope or time frame of a project, unforeseen conditions that require change, or a design error/omission that results in change | (пусто)
62 | A0069 | https://research.tees.ac.uk/ws/portalfiles/portal/24800290/Cost_benefit_analysis_of_BIM_enabled_design_clash_detection_and_resolution.pdf | Chahrour et al. (2020) | UK | 2020 | 1_Design | Cost saving from identifying clash detection | 20% | Reduction in the overrun of the total project construction value | 2.048% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,8_CAPEX reduction | Construction stage_CAPEX overrun |  | (пусто)
63 | A0070 | https://link.springer.com/article/10.1007/s42107-022-00451-x | Honnappa and Padala (2022) | India | 2022 | 2_Construction | Reduction in time of the schedule delay | 11.52% | Reduction in time of the construction schedule delay | 11.52% | 1:1 | Construction stage schedule_delay | The delay can be avoided due to the use of BIM | (пусто)
64 | A0071 | https://link.springer.com/article/10.1007/s42107-022-00451-x | Honnappa and Padala (2022) | India | 2022 | 2_Construction | Reduction of budget overrun of total project value | 8.16% | Reduction in the overrun of the total project construction value | 8.16% | 1:1 | Construction stage_CAPEX overrun |  | (пусто)
65 | A0072 | https://www.set-science.com/pdf_view.php?cacryn=SIAP2025&cid=100&pid=16&fv=SETSCI_SIAP2025_00100_0016 | Kocakaya et al. (2025) | Turkey | 2025 | 4_All stages | ROI | 580% | Return on investments (3) | 580% | 1:1 |  | Net BIM savings / Life cycle cost | (пусто)
66 | A0073 | https://www.researchgate.net/publication/388725098_The_impact_of_BIM_on_project_time_and_cost_insights_from_case_studies | Das et al (2025) | India | 2025 | 1_Design | Reduction in the number of the design errors | 55% | Reduction in the number of the design errors | 1.408% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,2_CAPEX reduction | Design stage_CAPEX | Reduction of the number of the design errors on the design stage | (пусто)
67 | A0074 | https://www.researchgate.net/publication/388725098_The_impact_of_BIM_on_project_time_and_cost_insights_from_case_studies | Das et al (2025) | India | 2025 | 2_Construction | Reduction of rework costs | 45% | Reduction in the cost of the rework | 4.608% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,8_CAPEX reduction | Construction stage_CAPEX | Due to the change of order rework needs to be done | https://www.naiop.org/research-and-publications/magazine/2022/summer-2022/development-ownership/how-rfis-and-change-orders-disrupt-multifamily-development-projects/ assume from that CoO is 12,8% of the project cost
68 | A0075 | https://www.researchgate.net/publication/388725098_The_impact_of_BIM_on_project_time_and_cost_insights_from_case_studies | Das et al (2025) | India | 2025 | 1_Design | Reduction of time needed for the budget estimation | 80% | Reduction in time to complete the design stage | 2.4% | Assumption: 3% of time is needed for the budget estimation | Design stage schedule |  | (пусто)
69 | A0076 | https://www.researchgate.net/publication/388725098_The_impact_of_BIM_on_project_time_and_cost_insights_from_case_studies | Das et al (2025) | India | 2025 | 2_Construction | Reduction in number of Request of information | 80% | Reduction in number of RFI | 1.28% | 1,6% of CAPEX is RFI_CAPEX reduction | Construction stage_CAPEX | A RFI is a formal written process in which parties clarify information gaps in construction documents (McGraw-Hill, 2008). Incomplete, unclear or outdated technical specifications, and the lack of buildability result in continuous RFIs thereby, interruptions to the work progress (Jarkas and Bitar, 2012; Rivas et al., 2011; Hasan et al., 2018). This creates friction between the architect/engineers and the contractor | https://www.naiop.org/research-and-publications/magazine/2022/summer-2022/development-ownership/how-rfis-and-change-orders-disrupt-multifamily-development-projects/ assume from that RFI is 1,6% of the project cost
70 | A0077 | https://www.researchgate.net/publication/388725098_The_impact_of_BIM_on_project_time_and_cost_insights_from_case_studies | Das et al (2025) | India | 2025 | 2_Construction | Reduction of budget overrun of total project value | 37% | Reduction in the overrun of the total project construction value | 37% | 1:1 | Construction stage_CAPEX overrun |  | (пусто)
71 | A0078 | https://www.researchgate.net/publication/388725098_The_impact_of_BIM_on_project_time_and_cost_insights_from_case_studies | Das et al (2025) | India | 2025 | 1_Design | Reduction in the number of changes of orders | 32% | Reduction in the number of changes of orders | 0.8192% | 12,8% of CAPEX is change of orders and on the design stage CoO is 1:0,2_CAPEX reduction | Design stage_CAPEX | A change order is usually the result of an owner-initiated change in the scope or time frame of a project, unforeseen conditions that require change, or a design error/omission that results in change | (пусто)
72 | A0079 | https://www.researchgate.net/publication/396874076_Integration_of_Building_Information_Modelling_BIM_and_Digital_Twins_for_Lifecycle_Cost_Optimisation_in_Mega_Projects | Dagmawi et al. (2025) | Ethiopia | 2025 | 3_Operation | Lifecycle cost savings | 40% | Return on investments (3) | 40% | 1:1 |  | Net BIM savings / Life cycle cost | (пусто)
73 | A0080 | https://www.researchgate.net/publication/392333416_Building_Information_Modeling_BIM_for_Cost_Control_and_Technical_Supervision | Luna et al. (2025) | Philippines | 2025 | 2_Construction | Reduction in time of the schedule delay | 10% | Reduction in time of the construction schedule delay | 10% | 1:1 | Construction stage schedule_delay | The delay can be avoided due to the use of BIM | (пусто)
74 | A0081 | https://www.researchgate.net/publication/392333416_Building_Information_Modeling_BIM_for_Cost_Control_and_Technical_Supervision | Luna et al. (2025) | Philippines | 2025 | 2_Construction | Reduction of budget overrun of total project value | 12% | Reduction in the overrun of the total project construction value | 12% | 1:1 | Construction stage_CAPEX overrun |  | (пусто)
75 | A0082 | https://www.researchgate.net/publication/392350768_Monetizing_Digital_Innovation_in_the_AEC_Industry_Real_Estate_Value_Creation_Through_BIM_and_BMS_Integration | Atencio et al. (2025) | Colombia | 2025 | 3_Operation | Annual cost savings | 5.81% | Annual reduction in overall FM expenditures | 5.81% | 1:1 | Maintenance obligations | annual cost saving related to the asset value | (пусто)
76 | A0083 | https://www.researchgate.net/publication/392350768_Monetizing_Digital_Innovation_in_the_AEC_Industry_Real_Estate_Value_Creation_Through_BIM_and_BMS_Integration | Atencio et al. (2025) | Colombia | 2025 | 3_Operation | Improvement in coordination between different departments | 3.28% | Annual reduction in salary expenditures | 0.492% | 15% of working time is wasted time | Salary | Not cumulative / American Productivity & Quality Center (APQC) and other studies often find that knowledge workers can spend 15-20% of their time | (пусто)
77 | A0084 | https://www.researchgate.net/publication/392350768_Monetizing_Digital_Innovation_in_the_AEC_Industry_Real_Estate_Value_Creation_Through_BIM_and_BMS_Integration | Atencio et al. (2025) | Colombia | 2025 | 3_Operation | Reduction of facility managment expenditures | 6.42% | Annual reduction in maintance expenditures | 6.42% | 1:1 | Maintenance obligations |  | (пусто)
78 | A0085 | https://www.researchgate.net/publication/392350768_Monetizing_Digital_Innovation_in_the_AEC_Industry_Real_Estate_Value_Creation_Through_BIM_and_BMS_Integration | Atencio et al. (2025) | Colombia | 2025 | 3_Operation | Reduction of facility managment expenditures | 11.32% | Annual reduction in maintance expenditures | 11.32% | 1:1 | Maintenance obligations |  | (пусто)
79 | A0086 | https://www.researchgate.net/publication/391712462_Exploring_the_Impact_of_BIM_on_Construction_Project_in_Reducing_Life_Cycle_Cost | Sharma et al. (2025) | India | 2025 | 2_Construction | Reduction of budget overrun of total project value | 10% | Reduction in the overrun of the total project construction value | 10% | 1:1 | Construction stage_CAPEX overrun |  | (пусто)
80 | A0087 | https://www.researchgate.net/publication/391712462_Exploring_the_Impact_of_BIM_on_Construction_Project_in_Reducing_Life_Cycle_Cost | Sharma et al. (2025) | India | 2025 | 2_Construction | Reduction time of the schedule | 28% | Reduction in time of the construction schedule | 28% | 1:1 | Construction stage schedule | The time, which is needed for the constraction, can decrease due to BIM | (пусто)
81 | A0088 | https://www.researchgate.net/publication/391712462_Exploring_the_Impact_of_BIM_on_Construction_Project_in_Reducing_Life_Cycle_Cost | Sharma et al. (2025) | India | 2025 | 1_Design | Reduction in the number of the design errors | 30% | Reduction in the number of the design errors | 0.768% | 12,8% of CAPEX is change of orders, change of orders leads to rework in 1:0,2_CAPEX reduction | Design stage_CAPEX | Reduction of the number of the design errors on the design stage | (пусто)
82 | A0089 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 3_Operation | Reduction in the number of losses of the inventory | 15% | Annual reduction in maintance expenditures | 4.5% | 30% of the maintenance is connected with materials | Maintenance obligations |  | AI
83 | A0090 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Reduction in the number of losses of the inventory | 15% | Reduction in the overrun of the total project construction value | 3% | Assume that 20% of CAPEX is material, 0,5% is loss of the inventory | Construction stage_CAPEX overrun |  | (пусто)
84 | A0091 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Savings in material procurement | 22% | Reduction in the total project construction value | 2.2% | Assumption | Construction stage_CAPEX |  | (пусто)
85 | A0092 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Reduction of logistics costs | 18% | Reduction in the overrun of the total project construction value | 1.8% | Assume that ligistics costs is 10% of the CAPEX | Construction stage_CAPEX |  | (пусто)
86 | A0093 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Reduction of error in stock management | 25% | Reduction in the overrun of the total project construction value | 0.5% | Assumption | Construction stage_CAPEX overrun |  | (пусто)
87 | A0094 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Cost saving in material ordering processes | 14% | Reduction in the overrun of the total project construction value | 0.07% | Assume that material ordering process is 0,5% of the CAPEX | Construction stage_CAPEX overrun |  | (пусто)
88 | A0096 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Reduction of budget overrun of total project value | 25% | Reduction in the overrun of the total project construction value | 25% | 1:1 | Construction stage_CAPEX overrun |  | (пусто)
89 | A0097 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Reduction in the amount of unnecessary material expanses | 15% | Reduction in the overrun of the total project construction value | 0.15% | Assumption | Construction stage_CAPEX overrun |  | (пусто)
90 | A0098 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Increase in productivity | 17% | Reduction in the construction schedule | 17% | 1:1 | Construction stage schedule | The time, which is needed for the constraction, can decrease due to BIM | (пусто)
91 | A0099 | https://onlinescientificresearch.com/articles/effects-of-bim-and-erp-integration-on-logistics-and-cost-management-in-largescale-construction-projects.pdf | Elbir U. (2025) | Turkey | 2025 | 2_Construction | Increase in productivity | 20% | Reduction in the construction schedule | 20% | 1:1 | Construction stage schedule | The time, which is needed for the constraction, can decrease due to BIM | (пусто)
92 | A0100 | https://www.researchgate.net/publication/363946164_Cost-Benefit_Analysis_of_Building_Information_Modeling_Implementation_in_Construction_Projects_Evidence_from_Iran | Azizi et al. (2022) | Iran | 2022 | 1_Design | ROI | 355% | Return on investments (1) | 355% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
93 | A0101 | https://www.researchgate.net/publication/363946164_Cost-Benefit_Analysis_of_Building_Information_Modeling_Implementation_in_Construction_Projects_Evidence_from_Iran | Azizi et al. (2022) | Iran | 2022 | 2_Construction | ROI | 1420% | Return on investments (1) | 1420% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
94 | A0102 | https://www.researchgate.net/publication/363946164_Cost-Benefit_Analysis_of_Building_Information_Modeling_Implementation_in_Construction_Projects_Evidence_from_Iran | Azizi et al. (2022) | Iran | 2022 | 1_Design | ROI | 506.1% | Return on investments (1) | 506.1% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
95 | A0103 | https://www.researchgate.net/publication/363946164_Cost-Benefit_Analysis_of_Building_Information_Modeling_Implementation_in_Construction_Projects_Evidence_from_Iran | Azizi et al. (2022) | Iran | 2022 | 2_Construction | ROI | 939.9% | Return on investments (1) | 939.9% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
96 | A0104 | https://www.researchgate.net/publication/363946164_Cost-Benefit_Analysis_of_Building_Information_Modeling_Implementation_in_Construction_Projects_Evidence_from_Iran | Azizi et al. (2022) | Iran | 2022 | 1_Design | ROI | 117.2% | Return on investments (1) | 117.2% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
97 | A0105 | https://www.researchgate.net/publication/363946164_Cost-Benefit_Analysis_of_Building_Information_Modeling_Implementation_in_Construction_Projects_Evidence_from_Iran | Azizi et al. (2022) | Iran | 2022 | 2_Construction | ROI | 1055% | Return on investments (1) | 1055% | 1:1 |  | Net BIM savings / Cost of BIM | (пусто)
98 | A0106 | https://www.sciencedirect.com/science/article/pii/S0926580515000485?via%3Dihub | Nath et al. (2015) | Australia | 2015 | 1_Design | Reduction in time to complete the design stage | 38% | Reduction in time to complete the design stage | 38% | 1:1 | Design stage schedule | 100% - Time with BIM / Time without BIM | (пусто)
99 | A0107 | https://www.researchgate.net/publication/363946164_Cost-Benefit_Analysis_of_Building_Information_Modeling_Implementation_in_Construction_Projects_Evidence_from_Iran | McConnell and Wang (2015) | USA | 2015 | 2_Construction | Reduction in the total project construction value | 1.5% | Reduction in the total project construction value | 1.5% | 1:1 | Construction stage_CAPEX |  | (пусто)
100 | A0108 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 2_Construction | ROI | 2.556% | Return on investments (2) | 2.556% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
101 | A0109 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 2_Construction | ROI | 2.4% | Return on investments (2) | 2.4% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
102 | A0110 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 2_Construction | ROI | 2.604% | Return on investments (2) | 2.604% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
103 | A0111 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 2_Construction | ROI | 1.08% | Return on investments (2) | 1.08% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
104 | A0112 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 2_Construction | ROI | 5.82% | Return on investments (2) | 5.82% | 1:1 |  | Net BIM savings / CAPEX | (пусто)
105 | A0113 | https://www.researchgate.net/publication/264627245_Capturing_the_ROI_of_All-in_Building_Information_Modeling_A_Structured_Approach | Stowe et al. (2015) | USA | 2015 | 2_Construction | ROI | 6.3% | Return on investments (2) | 6.3% | 1:1 |  | Net BIM savings / CAPEX | (пусто)